LAUNCH PLAYBOOK · ETEL GROUP · HAWASSA

ETEL Delivery & Ride

A step-by-step plan to take ETEL Delivery & Ride from a working platform to a paying business in Hawassa.

| Model | Commission | Payments | Launch |
| --- | --- | --- | --- |
| Two-sided marketplace | 5% per merchant order | Telebirr, bank, EtelPay | One district first |

THE BIG PICTURE

# Five phases from setup to scale

Timings are planning assumptions. Move to the next phase only when the exit check of the current one is met.

| When | Phase | Focus |
| --- | --- | --- |
| Weeks 1-2 | Foundations | Legal, licences, bank and Telebirr accounts; pricing and commission rules; support line and team roles |
| Weeks 3-6 | Build supply | Sign first merchants; recruit and vet couriers and drivers; train on the apps |
| Weeks 7-10 | Soft launch | One district with invited customers; fix issues daily; test payouts end to end |
| Weeks 11-20 | Grow | Open the city with public campaigns; promo codes and referrals; add merchant tools |
| Month 6+ | Scale | Cross-sell Gebeya and Taxi; corporate accounts; plan the next city |

STEP BY STEP

# Ten steps to launch

## 01  Lock the legal and financial base

Management · Weeks 1-2 · Output: licences, accounts, contracts

- Confirm business licence and any transport or delivery permits

- Open the bank account and confirm Telebirr merchant access

- Draft merchant, courier and driver agreements

- Decide who is responsible for finance, support and operations

- Set up accounting and daily reconciliation

- Buy insurance where required

## 02  Set pricing and commission

Finance · Weeks 1-2 · Output: price sheet

- Confirm the 5% merchant commission

- Set delivery fees by Hawassa zone

- Set ride fares: metered and fixed

- Decide courier and driver earning share

- Write refund and cancellation rules

- Enter all rates in the admin settings

## 03  Choose the launch district

Operations · Weeks 2-3 · Output: district map and target list

- Pick one dense district with many restaurants and shops

- List 60 candidate merchants and rank them

- Map pickup points and typical delivery distances

- Check road and traffic patterns

- Identify taxi stands and hotels for ride pickups

- Set the district border and delivery radius

## 04  Sign the first merchants

Merchant success · Weeks 3-6 · Output: 20 signed merchants

- Visit in person with a one-page offer

- Load menus, items and photos into the platform

- Give each merchant a login and a short training

- Agree preparation times

- Explain payouts and the 5% commission clearly

- Leave a printed quick guide and a support number

## 05  Recruit and vet couriers and drivers

Operations · Weeks 3-6 · Output: verified fleet

- Advertise through agents, taxi stands and social media

- Check ID, licence, vehicle and references

- Register each in the driver or courier app

- Train on accepting jobs, navigation and customer handling

- Explain earnings and how wallet payouts work

- Set a minimum-earnings guarantee for the first weeks

## 06  Test everything end to end

Product · Weeks 5-7 · Output: test report

- Place real small orders from every merchant

- Test every payment route: Telebirr, bank, EtelPay, cash if used

- Test payouts to merchant, courier and driver

- Test cancellations, refunds and failed payments

- Run a security check on admin and payment endpoints

- Take a full backup and rehearse a restore

## 07  Soft launch with invited customers

Growth · Weeks 7-10 · Output: first 200 orders

- Invite friends, staff and nearby offices with a promo code

- Watch every order live in the admin panel

- Call customers after delivery to collect feedback

- Hold a daily 15-minute review of problems

- Fix the top three issues each week

- Publish nothing publicly yet

## 08  Open to the public

Marketing · Weeks 11-14 · Output: public launch

- Launch on social media with a clear first-order offer

- Put posters at merchants, taxi stands and campuses

- Turn on referral rewards

- Announce through local media and community groups

- Feature the best merchants

- Add a welcome message in English and Amharic

## 09  Improve reliability and retention

Operations · Weeks 14-20 · Output: weekly scorecard

- Review the KPI table every week

- Remove merchants and drivers with poor ratings

- Reward top performers

- Add loyalty rewards and wallet top-up bonuses

- Shorten dispatch time with better courier positioning

- Prepare a stronger hosting setup

## 10  Expand

Management · Month 6+ · Output: growth plan

- Open more districts one at a time

- Add corporate accounts and merchant advertising

- Cross-sell Gebeya, Taxi and EtelPay

- Use the calculator to confirm profit per order

- Plan funding for the next city

- Update this playbook with real numbers

HOW IT WORKS

# The two core journeys

## Delivery order

Merchant share is the order value minus the 5% commission. The courier fee comes from the delivery fee.

## Ride

Platform keeps a share of each fare. The rate is still to be set.

WHY ETEL CAN WIN

# One identity, one wallet, many services

EtelID and EtelPay sit under every Etel app. A customer who signs up for delivery already has an account and a wallet for rides, the marketplace and taxi.

MONEY

# Unit economics

Example inputs only. Replace them with your real numbers before making decisions.

| Input (example) | Value |
| --- | --- |
| Average order value | 400 ETB |
| Commission on order | 5% |
| Delivery fee charged | 60 ETB |
| Courier share of fee | 80% |
| Orders per day | 100 |
| Payment fee per order | 3 ETB |
| Monthly fixed costs | 150,000 ETB |

| Result | Value |
| --- | --- |
| Commission per order | 20 ETB |
| Delivery margin per order | 12 ETB |
| Payment fee per order | -3 ETB |
| Contribution per order | 29 ETB |
| Monthly contribution (30 days) | 87,000 ETB |
| Monthly fixed costs | -150,000 ETB |
| Monthly result | -63,000 ETB |
| Break-even orders per day | 173 |

MEASURE

# What to track every week

Set a target for each metric with the team before the soft launch.

| Metric | Why it matters | How to measure | Target |
| --- | --- | --- | --- |
| Orders per day | Demand and revenue driver | Completed orders in the admin panel | [set] |
| Rides per day | Ride demand | Completed trips | [set] |
| Active merchants | Supply choice for customers | Merchants with at least one order in 7 days | [set] |
| Active couriers and drivers | Speed of pickup | Accounts online in 7 days | [set] |
| Minutes to delivery | Customer trust | Order placed to delivery confirmed | [set] |
| Repeat customers | Retention | Customers with 2 or more orders in 30 days | [set] |
| Cancelled or failed orders | Lost revenue and reputation | Cancelled divided by placed | [set] |
| Contribution per order | Profit health | Calculator, using real data | [set] |

BE READY

# Risks and how to handle them

| Risk | Level | What to do |
| --- | --- | --- |
| Too few couriers or drivers, so pickups are slow | High | Recruit ahead of demand, guarantee minimum earnings in the first weeks, launch one district only. |
| Merchants do not stay active | High | Weekly visits, fast payouts, show them their order numbers. |
| Payment or payout errors | High | Test payouts with small real orders before launch, daily reconciliation, clear dispute steps. |
| Platform downtime on shared hosting | Medium | Backups, uptime alerts, plan a move to stronger hosting before scaling. |
| Security and data protection | Medium | Keep audits current, limit admin access, review INSA findings. |
| Competitors copy prices | Medium | Compete on reliability and the one-login, one-wallet experience, not on discounts alone. |
| Regulation on wallets and ride-hailing | Medium | Confirm licences early with the relevant offices and get advice in writing. |

IDENTITY

# Brand kit

The mark is an E built from three bars, with a dotted route leaving it and ending at a location pin. It says both things the business does: it moves goods and people.

| Carbon | Gold | Bright gold | Cream |
| --- | --- | --- | --- |
| #0D0B08 | #D4AF37 | #F2CC6B | #F5EFE0 |

Type: Cormorant Garamond for headlines, DM Sans for text. Keep clear space around the mark equal to the width of one bar of the E.